## Sheet1
to be modified / finalised with the selected contractor
Construction Carambolas project plan |  | months to be determined depending on disbursment
Cluster | Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Preparatory phase | Hold project launch
Secure all the necessary permits - planning permission
Confirm pre-selected contractors
All contracts signed
Hold staff and beneficiary information session
Confirm project management, reporting and accounting tasks and procedures
Project promotion and visibility - FB, press release, etc.
Construction | Preparatory works - ground leveling, vegetation clearing etc.
Foundations
Core construction
Roofing
Internal fittings, fixture, painting
Systems and their connection
Landscaping
Furnishing and other equipment
Certification
Launch of additional services | New timetable
Beneficiaries on waiting list informed
New beneficiaries registered
Staffing secured for additional services
ToR or curriculum adopted for the new services
Budget for new services secured
Small equipment and materials for new services secured
Manage the project | Establish project bi-monthly meetings
Project coordination
Project audit
Project funding applications, crowdfunding etc. to secure co-funding sources and sustanibility funds
Opening ceremony with the Embassy's representation and its visibility
Write project reports